SHSCT ANNUAL STRATEGIC PLAN UPDATE

| STRATEGIC PRIORITIES | Progress as at November 2024 |
| --- | --- |
|  | - The Trust has drafted and submitted the first iteration of its Financial Recovery Plan to SPPG/DoH on 1st October which sets out indicative targets for financial recovery over the next 5 years. Work continues internally within the Trust and with SPPG colleagues to further refine the plan and a bilateral meeting has taken place on 30th October 2024. The final agreed Financial Recovery plan will be underpinned by detailed operational plans. - The Reform & Improvement, Savings & Efficiency (RISE) Programme Board was established in July 24 to deliver transformational change with a focus on service reform and improvement and delivering savings and controlling costs. There are currently 41 savings projects across the Trust that have delivered over £5.5m of savings to date. - One of the key projects under the RISE Programme is Timely Care. The Trust is working with the Regional Coordination Centre (RCC) partners to deliver the Timely Care project objectives which aims to transform the delivery of unscheduled care and ensure provision of safe, effective and timely care at each stage of the patient journey. |
|  | - Progress in implementation of the Review of Financial Governance recommendations – c90% of the recommendations noted in the review have been completed to date with all on target to complete by the 31st March 2025. Recommendations completed to date include completion of Financial Plan for 24/25, first submission of Financial Recovery plan to SPPG/DoH, inception of RISE savings programme and governance structure, new format of SLT/Trust Board report, appointment of Critical Friend, updated SLT/TB cover sheet, Directorate Accountability meetings, enhanced budget setting process for 24/25 and internal review of Finance structures. - Financial management skills are being developed across the Trust as follows; - 1108 managers have been trained on Financial Management as part of the Insights for Managers Programme Module 1. - Collaborative Planning (CP) Refresher Training Programme being delivered during Sept 24 - March 25 and specific one to one CP budget manager training provided where requested. - Finance Training for Board Members and Directors delivered on 27th June 2024. - Programme of Financial Management Training scheduled for roll out to all staff who manage a budget starting 19th November 2024, six sessions scheduled to take place. - Healthcare Financial Management Association (HFMA) financial training modules will be available for completion by budget holders from December 2024 for completion by March 2025 |
|  | - Encompass ‘go live’ scheduled for 8th May 2025. An extensive programme of preparation and training is underway as part of the Encompass Programme which is on schedule and on budget. The Trust is also providing support to other Trusts as part of their implementation of Encompass. - The Equip Programme is a HSCNI wide programme to replace the existing HR and Finance systems (HRPTS and FPL) with a new modern and user-friendly system to support the delivery of Finance, Human Resources, Payroll, PaLS and Systems Administration activities. The Trust Equip Readiness Group has been established and reports to the Trust Strategy and Transformation Committee. HROD and Finance staff have been heavily involved in pre-design work for equip and work has progressed to the ‘design’ phase as the Systems Integration partner joined in September 2024 with staff ‘subject matter experts’ supporting design and build workshops. The current timeline of the design phase is mid November 2024 through to the end of May 2025. New governance structures have been developed which will provide key HROD and Finance stakeholders with an opportunity to input into functional decision making. |
|  | - Sustainability Waste and Carbon Committee has been established and meeting regularly. - Bluestone Unit has been recognised with a sustainability award. - The Trust has invested around £5m in Estates projects to reduce carbon emissions. - A pilot booking system for hot desking has commenced which will aim to identify efficiencies in use of space. - In partnership with the Woodland Trust, trees are being planted on the St Lukes Hospital site. - Biodiversity strategies have been implemented across eight Trust sites. - An application has been lodged for chartered status in relation to biodiversity. - Work has commenced on Sustainability plan 2030 |
|  | - Integral to the development of the Trust Vision & Strategy 2030, the Trust has an established a Senior Leaders network and a Community of Leaders Forum. - All Directorates have shared and continue to promote within their teams the Trusts set of Guiding Principles. - Working Together Hubs have been established to embed service user and carer involvement and feedback at all levels bringing together staff, service users and carers to plan and action service improvements through an inclusive approach to improve services, experience and outcomes for everyone. There are currently a total of 20 active projects in 4 operational Directorates. - A total of 267 staff and service users have participated in Patient and Public Involvement (PPI) training between April and September 2024. Currently, the number of service users reps registered for involvement is 83. - The Involvement Champion role was launched during involvement week in July 2024. As of October 2024, 12 staff have received induction training into this role. - Children and Young People Autism Service have implemented a Shared Decision Making Pilot using patient decision aids. |
|  | - 37 Staff Well Being Champions have been recruited across the Trust. - As at 30.09.2024, 45% of Trust Staff had recorded appraisal conversations. - In year, the Trust has rolled out all four modules of the Managers Insights Programme with 91% attendance at Module 1, 90% attendance at Module 2, 89% attendance at Module 3 and currently 75% attendance at Module 4. - A work-stream has been established to review and implement recommendations from the Baseline Assessment Tool [NICE NG212] Mental wellbeing at work. - A Pilot Wellness in the Workplace Group has been established with Occupational Health and Well Being Psychology Service. - An enhanced induction programme for international staff has been developed and rolled out. - A Disability Advocate has been appointed to represent and support the needs of staff with disabilities and long-term health conditions. |
|  | - The Timely Care Programme is aimed at transforming the delivery of unscheduled care services, focusing on the three main themes of Admissions Avoidance, Flow and Discharge. Progress is as follows; - Establishment of Programme Steering Group reporting to the RISE Programme Board. - Establishment of 3 main Pillars to lead improvements in Admissions, Flow and Timely Discharge. To date, there are 19 projects across the workstreams. Improvements in Lab Processes have been achieved, Primary Care Screening at the Front Door is due to commence on 11th November 2024, the Single Discharge Team has been established, a number of ambulatory pathways are being worked up and a model has been agreed for the implementation of Frailty at the Front Door which is an interface service meeting the needs of frailty patients in the Emergency Department. Work is also being undertaken to improve flow in wards, improve timely access to diagnostics and to enhance provision of community based care. - Daisy Hill Hospital Stabilisation - The stabilisation of DHH continues to progress through the implementation the new medical model and a range of hospital and community measures to provide alternative pathways to hospital admission; namely enhancement of Acute Care at Home in the Newry and Mourne locality, Community rehabilitation, and Same Day Emergency Care (SDEC) models of care. |
|  | - The Out-Patient Modernisation project is established with the aim to ensure integrated transformation and shared learning within Out-patient modernisation work. There are eight workstreams within the project with a number of these in parallel with the Regional Out-Patient Modernisation Project and its sub-groups for Enhanced Clinical Triage and Patient Initiated Follow-Up. - To date five of the eight workstreams have completed which focused on: ENT referral pathways, Envoy text messaging system, Integrated Elective Access Protocol (IEAP), Out-patient room utilisation and ENT QR code waiting list validation. - Non recurrent waiting list initiative funding of £15M has been allocated to the Trust. As at September 2024, 13,435 people have been removed from a waiting list. - Service Delivery Plan Performance monitoring continues. There are 14 Service Delivery Plan areas containing 69 individual service metrics/outcomes. The cumulative information from April – September 2024 shows that 61% of measures are either on track or partially on track. - A Theatre Recovery Plan which includes Paediatrics is in place with the aim of achieving commissioned levels of activity by the close of financial year 2024/25, work is ongoing. Significant work has been undertaken to provide training and support for more junior theatre nurses to achieve capability, competence, and confidence. - The Trust has representation on and contributes to both the Regional Cancer Strategy Programme Board and Steering Group Communications training has been delivered to Cancer Nurse Specialists Trust wide. - Work is progressing on the Rapid Diagnostics Centre on the South Tyrone Hospital Site. Estates works are due to commence in November 2024 and it is expected that the centre will be operational from March 2025. - The number of people waiting for Community Mental Health Services more than 13 weeks reduced by <29% since April 2024 (from 1064 to 757) |
|  | - The stabilisation of DHH continues to progress through the implementation of a range of hospital and community measures to provide alternative pathways to hospital admission. - As part of the Timely Care Programme, the following initiatives are in development and implementation; - Work has commenced with NIAS and Nursing Home providers to develop alternatives to hospital for frail and elderly patients. - Enhancement of Acute Care at Home Trust wide. - Urgent Care Centre GP ‘Screening at the Front Door’ to commence at CAH from 11th November to reduce avoidable ED attendances. - Day Opportunities attendance for Adults with a Learning Disability has increased from 1072 in April 2024 to 1383 in September 2024. The number of groups facilitated by Day Opportunities has increased from 4 to 11 in October 2024. The horticulture unit, working with the Estates Team has increased the number of placements available each day from 12 to 24 across the 5 days by comparison to April 2024. - Community Mental Health Addictions Team have facilitated 17 service users to complete Alcohol detox in the community since April 2024 reducing the need for hospital admission for alcohol detox. - The Community Mental Health Services project continues to achieve outcomes necessary to achieve full integration of the Primary Mental Health Care and Support and Recovery Teams. This project will improve service provision through a model which is evidence based, reflects best practice, provides the highest standards of assessment, treatment, care and support to service users and carers and promotes consistency and equity of access for people in need of psychological therapy & mental health services. |